## WorkTracker
Sl No | Work Description | Remarks | Status | Next Action required | Priority | Category | BOQ | Design Completed
1 | Water drain gutter for roof top of room, new roof, and for old clay structure to stop water entering neighbour house. |  | Discussed | Implementation pending | Low | fabrication | ? | Yes
2 | window Sajja for gnd floor, first floor, 2nd floor and roof top room | To be checked if 2nd floor requires it | decision pending | To be decided | Low | fabrication | ? | Yes
3 | Automatic water level control | Plumer should evaluate if it is working , otherwise buy new one. | decision pending | To be decided | low | plumbing | ? | Yes
4 | Water pump covering | Submersible Pump purchased | Discussed | Implemented | low | civil | Included | Yes
5 | MBR toilet duct and False ceiling |  | Discussed | False Ceiling and Core Cuting Pending | high | civil | Included | Yes
6 | Sliding mirror in MBR and kids room |  | Discussed | To be updated in drawing and Render | low | carpentry | Included | Yes
7 | Terrace door clousure | Will use sliding MS Door for the Entrance | Discussed | To be installed | medium | fabrication | Included | Yes
8 | Security main door grill | Existing design has one rod running in between, discussed to make it two. | Discussed | Updated in render and Drawing, Installation Pending | medium | fabrication | Included | Yes
9 | Main door | very simple design with one line | Discussed | Drawing updated, Laminate Selection for the Door Pending | medium | carpentry | Included | Yes
10 | Balcony railings | Height to be increased for safety concerns | Discussed | Design Completed, to be installed on site | medium | fabrication | ? | Yes
11 | I beam | I beam to be hidden | Discussed | Design Completed, Confirmation Pending | high | carpentry | ? | yes
12 | CCTV connection | Connection to be planned and provided | discussed | Implementation pending | low | electrical | ? | Almost
13 | Janitor closet |  | discussed | Updated in the render, to be implemented | medium | carpentry | Included | Yes
14 | Window grills | Fabrication over for all windows | discussed | To be Installed | medium | fabrication | Included | Yes
15 | Separation for aquaguard and dustbin |  | discussed | To be updated in drawing | medium | carpentry | ? | No
16 | Hidden drawer in MBR |  | discussed | To be updated in drawing | medium | carpentry | ? | No
17 | UPS point connection at front of dor or near TV |  | To be discussed | To be designed | medium | electrical | ? | No
18 | Slope near parking |  | discussed | Implementation pending | low | civil | ? | yes
19 | Ground floor window fitment | reuse existing window | wall contructed | Implementation pending | low | civil | To be excluded | yes
20 | Ground floor storage room door fitment |  | discussed | Implementation pending | low | civil | Already included | Yes
21 | Ground floor bathroom rework | upgration from Indian to westren | cement floor is put | Implementation pending | medium | plumbing | Already included | Yes
22 | Ground fllor MBR wall tile rework | removal of tiles, wet walls seen | plastering done | Implementation pending | high | plumbing | Already included | yes
24 | Ground floor : Pooja to storage conversion |  | design pending | To be designed | medium | carpentry | ? | No
25 | First floor bathroom rework | upgration from Indian to westren | cement floor is put | Implementation pending | medium | plumbing | Already included | Yes
26 | First floor : Pooja to storage conversion |  | design pending | To be designed | medium | carpentry | ? | No
27 | Wifi connection at second floor | Optical wire is requested from JIO, to be routed near TV | discussed | Implementation pending | medium | electrical | Already included | yes
28 | Solar pipe replacement | new pipe to be put only for 2nd floor | discussed | Implementation pending | low | plumbing | To be included | yes
29 | Floor polish for gnd and 1st floor |  | discussed | Implementation pending | low | painting | Included | yes
30 | new ms rods insertion in between rods in balcony of 2nd floor and damaged rod to be removed | For security | discussed | Implementation pending | low | fabrication | ? | yes
31 | roof top nwindow insertion | existing window can be reused | discussed | Implementation pending | low | civil | ? | yes
32 | roof top flooring | floor mat to be put | discussed | Implementation pending | low | civil | ? | yes
33 | Relocating T links in roof top for drying clothes | Existing T links to be relocated | discussed | Implementation pending | low | fabrication | ? | yes
34 | Material Selection | Wash basin , kitchen sink, electrical switch, lights etc | Tiles, Sanitory and Laminates selected | Wash basin , kitchen sink, electrical switch catalog required. Laminate required , commode for gnd 2nd roof top Shaving mirror to be selected | low |  | Already included | yes
35 | pooja unit | Unit in line with existing first floor to be done | discussed | Design to be updated | high | carpentry | Already included | No
37 | window design of balcony | wodden beading with opaque glass | discussed | Design to be updated | high | carpentry | Already included | No
38 | shoe rack | bench required | discussed | Design is Updated. Implementation pending | high | carpentry | Already included | Yes
39 | terrace electical points | As shown in design | discussed | Implementation pending | Low | electrical | Already included | yes
40 | Name board for the house | To be sourced | To be discussed | To be decided | low | civil | To be included | no
41 | Mobile charging sockets | to be increased to 6 in kids bed room, Additional 3 required in Roof terrace | To be discussed | Implementation pending | low | electrical | ? | no
42 | Sun Protection sheets near washing machine | 2nd floor | To be discussed | Implementation pending | low | civil | ? | no
43 | AEH point for room geyser | To be checked if availble | To be discussed | To be decided | high | electrical | ? | no
44 | Grounding roof structure | lighting arrestor can be planned | To be discussed | To be decided | high | electrical | ? | no
45 | Roof top water drain slope to be reworked | existing drain blocked by metal roof | To be discussed | To be decided | high | civil | ? | no

## Sheet2
0